## Sheet1
PLAYWINK SPORTS UNLIMITED
Identified By: ANANDU AJITH Version No: Reported No: Environmental details: Date:27/01/2022
Bug Id | Expected Result | Bug Description | stepstoreproduce | severity | priority | screenshot | status
PSU_01 | Should work the Box Cricket booking function in the Book Page | the Box Cricket booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select box cricket | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1gbsOpmsw7M7Do5AAVapI8OggQmM4GVWc/view?usp=share_link | NEW
PSU_02 | Should work the Tennis booking function in the Book Page | the Tennis booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Tennis | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1_PXNnxvUOFspXGG5ly0zBwU5o3vJz1GU/view?usp=share_link | NEW
PSU_03 | Should work the Paddle Tennis booking function in the Book Page | the Paddle Tennis booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Paddle Tennis | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1_PXNnxvUOFspXGG5ly0zBwU5o3vJz1GU/view?usp=share_link | NEW
PSU_04 | Should work the Badminton booking function in the Book Page | the Badminton booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Badminton | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1Dh9JlXTG_FQ92AvPCj2umbCfPUoL7Wr7/view?usp=share_link | NEW
PSU_05 | Should work the Table Tennis booking function in the Book Page | the Table Tennis booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Table Tennis | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1-GVrLORBME3q9ilZdn73LLmnXVuHjNTq/view?usp=share_link | NEW
PSU_06 | Should work the Football booking function in the Book Page | the Football booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Football | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/16HWClrbdJngOO7hgLKEYbVygToOvqM1g/view?usp=share_link | NEW
PSU_07 | Should work the Hockey booking function in the Book Page | the Hockey booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Hockey | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1n1e0uMSSMKX5AiNQmjPhD3UM5wAUKd0r/view?usp=share_link | NEW
PSU_08 | Should work the Archery booking function in the Book Page | the Archery booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Archery | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1Nb_4RhFnkIPWV9q31i5hWoHDYXfQHytH/view?usp=share_link | NEW
PSU_09 | Should work the Adventure Sports booking function in the Book Page | the Adventure Sports booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Adventure Sports | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/1fS1EllQokGmS7-KtD-nrxGCCe5RzaprM/view?usp=share_link | NEW
PSU_10 | Should work the Swimming booking function in the Book Page | the Swimming booking function in the book page is not displaying available venues | 1.open the app 2.select book page 3.select Swimming | MAJOR | HIGH PRIORITY | https://drive.google.com/file/d/11hUIfpsrf2CJDWUTaED6uVKPbECtI4r2/view?usp=share_link | NEW
PSU_11 | Should work the cancellation policy function in the profile | the cancellation policy function is working and directing to the next page | 1.open the app 2.select profile page 3.select cancellation policy | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1L7nbWgfHlyBmowkB1G-gXCogMantX5ww/view?usp=share_link | NEW
PSU_12 | Should work the help and support function in the profile | the help and support function is working and directing to the next page | 1.open the app 2.select profile page 3.select help and support | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1l665py25o4tdGOCX84GqTwh5V5Gc3azY/view?usp=share_link | NEW
PSU_13 | Should work the refer and earn function in the profile | the refer and earn function is working and directing to the next page | 1.open the app 2.select profile page 3.select refer and earn | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1Oj2KIJAoWvEllt2jRF7GoOa0r9jfkvwm/view?usp=share_link | NEW
PSU_14 | Should work the Favourite function in the profile | the Favourite function is working and directing to the next page | 1.open the app 2.select profile page 3.select Favourite | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1quUxQ3FvQN6dyoBBvQZ5LwRkUFDtf_Vg/view?usp=share_link | NEW
PSU_15 | Should work the wallet function in the profile | the wallet function is working and directing to the next page | 1.open the app 2.select profile page 3.select wallet | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1Qfn1jU88lQWLPscb0VPXRxUJY2Lks4vj/view?usp=share_link | NEW
PSU_16 | Should work the NOTIFICATION function in the profile | the NOTIFICATION is working and directing to the next page | 1.open the app 2.select profile page 3.select NOTIFICATION | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1OggC7r3wigJugsFL3EuDKeJqpzhEnZhU/view?usp=share_link | NEW
PSU_17 | Should work the ABOUT function in the profile | the ABOUT is working and directing to the next page | 1.open the app 2.select profile page 3.select ABOUT | MINOR | LOW PRIORITY | https://drive.google.com/file/d/10zT2L5N6U00mjK4Nu36XW8fudYbUhV7L/view?usp=share_link | NEW
PSU_18 | Should work the UPDATE PROFILE function in the profile | the UPDATE PROFILE is working and directing to the next page | 1.open the app 2.select profile page 3.select UPDATE PROFILE | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1-_RlE12wWoE58hvJg098BascmkF0lppO/view?usp=share_link | NEW
PSU_19 | Should work the LOCATION function in the Home Pge | the LOCATION is working and directing to the next page | 1.open the app 2.select home page 3.select LOCATION | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1ZDVoZL7DFMBgFmx99Zv9KbJbUCf2Ix7I/view?usp=share_link | NEW
PSU_20 | Should work the see all venues function in the Home Page | the see all venues is working and directing to the next page | 1.open the app 2.select profile page 3.select see all venues | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1VK3ckmN700-q6RLOwJC3Wwgfoa5WiTbP/view?usp=share_link | NEW
PSU_21 | Should work the BUY function in the Home Page | the buy is working and directing to the next page | 1.open the app 2.select BUY page | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1N-30OFNi8lmtqMKTAV7rsudpJduFyKaq/view?usp=share_link | NEW
PSU_22 | Should work the LEARN function in the Home Page | the learn is working and directing to the next page | 1.open the app 2.select LEARN page | MINOR | LOW PRIORITY | https://drive.google.com/file/d/1cnQwihkD6KvY2rdE-rS4Kr9ITabzzX0Q/view?usp=share_link | NEW